## May 2016
GOA SHIPYARD LIMITED
SHIPYARD MODERNISATION CELL
CIVIL ENGINEERING SECTION
List of orders placed for Month of May - 2016
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Sr.no | Tender No | Item/Nature of Work | Mode of Tender Inquiry | Date of Publication of NIT | Type of Bidding (Single/ Two bid system | Last Date of Receipt of Tender | Nos of Tenders Received | Nos & name of parties qualified after Technical evaluation | Nos & name of parties not qualified after Technical evaluation | Whether contract awarded to lowest tenderer/ Evaluated L1 | Contract No. & Date | Name of Contractor | Value of Contract Rs. | Scheduled date of completion of Supplies | Date of letter of award
1 | ETN-035 | Replacement of roofing & false ceiling at GSL unit II | E-Tender | 2016-09-03 | Two Bid | 2016-08-04 | 3 | 1) M/s. Ekta Enggineering Works 2) M/s. Atlantic Waterproofing Co.(GOA) 3) M/s.Deepak Engineers & Contractors | Nil | Yes | 901250 Dt. 02-05-2016 | M/s. Ekta Enggineering Works | 2345573 | 18-07-2016 | 21-04-2016
2 | 82-S | Waterproofing Treatment to expansion joint in the roof of canteen Building | Limited Tender | 23-03-2016 | Single Bid | 2016-12-04 | 2 | 1) M/s. Geo Construction 2) M/s. Atlantic Waterproofing Co. (GOA) | Nil | Yes | 901251 Dt. 10-05-2016 | M/s. Geo Construction | 60000 | 27-05-2016 | 19-04-2016
3 | ETN-038 | ARC repairs/replacement of AC sheeting & allied works inside & outside the yard 2016-17 | E-Tender | 16-02-2016 | Two Bid | 29-04-2016 | 2 | 1) M/s. Deepak Engineers & Contractor 2) M/S. Alpha Engineers | Nil | Yes | 901252 Dt. 20-05-2016 | M/s. Deepak Engineers & Contractor | 1398073 | 19-05-2017 | 2016-12-05
4 | TN-324 | Repair works at Trupti Apartment, New Vaddem | Open Tender | 17-02-2016 | Two Bid | 2016-01-04 | 3 | 1) M/s. Murali Builders 2) M/s. Atlantic Waterproofing Co.(GOA) 3) M/s. Shreeram Enterprises | Nil | Yes | 901253 Dt. 24-05-2016 | M/s. Murali Builders | 248152 | 2016-09-07 | 28-04-2016
5 | 82-X | Replacement of broken glass at Shiplift Control Room | Limited Tender | 20-04-2016 | Single Bid | 22-04-2016 | 3 | 1) M/s. Surya Enterprise 2) M/s. Crystal Ball 3) M/s. Shreeram Enterprises | Nil | Yes | 901254 Dt. 24-05-2016 | M/s. Crystal Ball | 23400 | 2016-07-06 | 2016-06-05
6 | 82-K | Renovation of QA Staircase. | Limited Tender | 2016-09-02 | Single Bid | 29-04-2016 | 2 | 1) M/s. Prem Enterprises 2) M/s. Murali Builders | Nil | Yes | 901255 Dt. 25-05-2016 | M/s. Murali Builders | 54777 | 24-06-2016 | 2016-03-05
7 | ETN-038 | Renovation to toilet & miscellaneaus works at CISF barrack sada | E-Tender | 2016-01-03 | Two Bid | 2016-08-04 | 2 | 1) M/s. Murali Builders 2) M/s.Atlantic Waterproofing Co. (GOA) | Nil | Yes | 901256 Dt. 27-05-2016 | M/s. Murali Builders | 857155 | 27-07-2016 | 25-04-2016